## Sheet1
PROJECT NAME : Lubricant
S.NO | Pages | Changes | Effort | Delivery Date | Actual Completed Date | status | Remarks
Admin Panel Modules
1 | Admin Panel | Staticpage Content /unique validation | 1hr | 2018-06-10 | 2018-07-10 | intiated
2 | Admin Panel | Information Management/duplicate record. | 2 hr | 2018-06-10 | 2018-07-10 | intiated
3 | Admin Panel | Add user page/fields without empty | 2hr | 2018-06-10 | 2018-07-10 | intiated
4 | Admin Panel | Should have some data, regarding total product or some information | 2hr | 6/10/2018 | 2018-07-10 | intiated
5 | Admin Panel | Edit user/unique validation | 1hr | 2018-06-10 | 2018-07-10 | intiated
6 | Admin Panel | footer text not removed. |  | 2018-06-10 | 2018-06-10 | Completed
Total Hours |  |  | 8 hrs